## Sheet1
To edit this Gantt Chart: | Enter assumptions into the light orange boxes. I have inserted very broad guesses as to how long each step might require for an RPC.
Edit the start and end date formulas to change any assumptions about which tasks are completed concurrently.
Adjust assumptions if timing puts tasks within the winter break holidays (e.g. from Christmas to New Years).
Note: the dates do not reflect number of business days and interaction with weekends, so some of them have been padded with a few extra days.
Color code: | Input
Steps likely to start concurrently
Milestone date
Phase | Task | Start Date | End Date | Duration (days) | What organization? | Who specifically? | Notes | Status
Research and engagement | Decide on scope of fleets to engage (public, private, and/or individuals) | 2016-12-01 | 2016-12-05 | 5 | the RPC
Research and engagement | Invite interested and influential parties to a stakeholder group | 2016-12-06 | 2016-12-12 | 7 | the RPC
Research and engagement | Meet with stakeholder group to establish goals | 2016-12-13 | 2016-12-20 | 7 | the RPC |  |  |  | <-- Note: I assume no work gets done between 12/20 and 1/3. You can change this.
Requirement identification | Gap analysis of what AFVs stakeholders are interested in but cannot yet purchase at acceptable prices | 2017-01-19 | 2017-01-28 | 10 | the RPC |  | BC can help
Requirement identification | Determine participating fleets' upcoming replacement needs | 2017-01-19 | 2017-01-28 | 10 | the RPC
Requirement identification | Determine which fleets are procuring the same types of vehicles | 2017-01-19 | 2017-02-02 | 15 | the RPC
Requirement identification | For each vehicle type, determine which specs are acceptable to a wide range of fleets (additional stakeholder meetings) | 2017-02-03 | 2017-02-17 | 15 | the RPC |  | We should limit types of vehicles
Requirement identification | Finalize a list of vehicles types to include for bids | 2017-02-18 | 2017-02-18 | 1 | the RPC |  | BC can help
Market analysis | Research product availability | 2017-02-19 | 2017-03-20 | 30 | the RPC w/assistance from Tech Coordinators
Market analysis | Determine local operational and infrastructure requirements for each vehicle type's deployment | 2017-02-19 | 2017-03-20 | 30 | the RPC w/assistance from Tech Coordinators
Market analysis | Confirm product availability and supplier/vendor capacity to deliver in your local context | 2017-02-19 | 2017-03-20 | 30 | the RPC w/assistance from Tech Coordinators
Market analysis | Develop vendor outreach plan, prep vendors for the RFP release | 2017-03-07 | 2017-04-18 | 42 | the RPC w/assistance from Tech Coordinators
Bid execution | Draft RFP | 2017-03-21 | 2017-04-03 | 14 | the procurement contact |  | BC and Stephe Yborra could help
Bid execution | Receive stakeholder feedback on RFP | 2017-04-04 | 2017-04-08 | 5 | the RPC
Bid execution | Edit RFP | 2017-04-09 | 2017-04-15 | 7 | the procurement contact
Bid execution | Issue bid | 2017-04-16 | 2017-04-18 | 3 | the procurement contact
Bid execution | Advertise RFP in trade magazines | 2017-04-19 | 2017-05-09 | 21 | the RPC w/assistance from Tech Coordinators |  | BC and Stephe Yborra could help
Bid execution | Advertise RFP through local channels | 2017-04-19 | 2017-05-09 | 21 | the RPC w/assistance from Tech Coordinators |  | BC and Stephe Yborra could help
Bid execution | Receive clarification questions from vendors, on question due date | 2017-05-10 | 2017-05-10 | 1 | the procurement contact
Bid execution | Discuss questions and issue clarifications | 2017-05-11 | 2017-05-14 | 4 | the procurement contact
Bid execution | Provide time before bid due date for vendors to adjust proposals based on questions | 2017-05-15 | 2017-05-18 | 4 | the procurement contact
Bid execution | Receive bids on bid due date | 2017-05-19 | 2017-05-19 | 1 | the procurement contact
Bid execution | Evaluate bids | 2017-05-20 | 2017-05-26 | 7 | TBD |  | BC can help
Bid execution | Interview and negotiate with vendors | 2017-05-27 | 2017-06-09 | 14 | the RPC and/or procurement contact |  | BC can provide guidance on this
Award and contract | Draft contract for services | 2017-06-10 | 2017-06-23 | 14 | the RPC and/or procurement contact
Award and contract | Revise based on stakeholder feedback and based on vendor feedback | 2017-06-24 | 2017-06-30 | 7 | the RPC and/or procurement contact
Award and contract | Execute master agreements | 2017-07-01 | 2017-07-01 | 3 | the RPC and/or procurement contact
Contract promotion | Post contract on web portal | 2017-07-04 | 2017-07-04 | 1 | the procurement contact
Contract promotion | Advertise to buyers through local channels, allow buyers to purchase off the contract. | 2017-07-05 | 2018-07-04 | 365 | all parties |  | Yes, agreed we should all work on this
Evaluation | Perform quarterly evaluation | 2017-10-02 | 2017-10-15 | 14 | the RPC
Formulas:
Start Date = [Start Date, row below]-[Duration (days)]
Start Date = [End Date]-[Duration (days)]
End Date = [Start Date]+[Duration (days)]-1
Note on G11: Philip Kreycik: Note. These can be changed based on however each RPC/COG is planning their work and whether they have a separate procurement office they are engaging deeply in the project. Just my best guesses.
Note on C15: Philip Kreycik: It is perfectly acceptable under this grant to invest effort in promoting existing contracts for whatever AFVs are already available at good prices.
Note on F28: Philip: Assume we want vendors to see this in the publication at least 2 weeks in advance and assume it takes at least a week to get into the magazine?